# Automation Handoff Plan — Kurt + Jessa

Date: 2026-04-05

Purpose: Make the Director Transition real by automating everything that currently requires Kurt's hands-on involvement. Two tracks: Kurt's ops automation (inventory, demand, POs) and Jessa's CS automation (reporting, tagging, escalation).

Principle from the Director Transition Playbook: "If someone can do a task 70% as well as you, delegate it. Your 100% on one reship approval is worth less than your 100% on a system that handles all reship approvals."

---

# The Current State (Why You're Stuck)

| Task | Who Does It Now | Time/Week | Should Be |
| --- | --- | --- | --- |
| Demand calculation | Kurt (manual) | 2-3 hrs | System (auto-sync + curation floor) |
| Cut order generation | Kurt (manual XLSX) | 2 hrs | System (one-click approve) |
| Shortage detection | Kurt (Slack DMs) | 1-2 hrs reactive | System (2-week alerts) |
| PO decisions | Kurt + Dan (Slack) | 1-2 hrs | Tommy (auto-drafted POs) |
| Reship decisions | Kurt (tagged in Slack) | 3-5 hrs | Jessa's team (Decision Guide) |
| Swap decisions | Kurt (manual calc) | 1-2 hrs | System (suggested swaps) |
| CS reporting | Jessa (manual spreadsheet) | 2-3 hrs | System (auto-generated) |
| Food safety tracking | Jessa (manual) | 1 hr | System (Gorgias sync) |
| Recipe rotation | Kurt (manual settings) | 1 hr/month | Tommy (recipe diff + auto-ramp) |

Total Kurt ops time today: ~15-20 hrs/week

Total after automation: ~2-3 hrs/week (review + approve)

---

# Track 1: Kurt's Automation (Inventory + Demand + POs)

## Already Built (This Session)

| Tool | Endpoint | What It Replaces |
| --- | --- | --- |
| Curation Floor | `/api/curation_floor` | Manual shortage detection |
| EWMA Forecast | `compute_ewma()` in shopify_sync | Flat 8-week average |
| Growth Multiplier | `compute_growth_multiplier()` | No acquisition signal |
| Final Demand | `/api/demand_final` | Manual demand calculation |
| PO Drafts | `/api/po_draft` | Kurt+Dan Slack PO discussions |
| PO Approve | `/api/po_approve` | Manual PO tracking |
| Recipe Diff | `/api/recipe_diff` | Manual demand impact guessing |
| Recipe Apply | `/api/recipe_apply` | Manual settings update |
| Auto-Depletion Journal | journal entries in `auto_deplete` | Dual inventory truth |

## What Kurt Does Now (Director Mode)

| Day | Action | Time | Tool |
| --- | --- | --- | --- |
| Monday | Scan PO draft — Tommy already approved? Confirm. | 5 min | `/api/po_draft` dashboard |
| Monday | Check shortage alerts — anything red? | 5 min | `/api/curation_floor` dashboard |
| Wednesday | Approve cut order — one click | 10 min | Auto-generated XLSX |
| Wednesday | Review swap suggestions if shortage | 10 min | `/api/suggest_fixes` |
| Friday | Glance at weekly ops summary | 10 min | Auto-report |
| **Total** |  | **~40 min/week** |  |

## What Kurt Does NOT Do

Calculate demand (system does it)

Build cut orders (system generates)

Chase Tommy for POs (system alerts him)

Approve individual reships (Jessa's team decides)

Monitor Slack for shortages (system alerts 2 weeks ahead)

Manually track inventory (journal-based ledger)

---

# Track 2: Jessa's Automation (CS Reporting + Tagging)

## Tools Already Built

| Tool | What It Does | Trigger |
| --- | --- | --- |
| `gorgias_sync_operational_issues` | Pulls tagged tickets → Google Sheet | MCP / scheduled |
| `gorgias_sync_food_safety` | Pulls spoiled/quality tickets → Sheet | MCP / scheduled |
| `enrich_operational_issues` | Fills carrier, state, FC from Shopify | MCP / scheduled |
| `rebuild_ops_summary` | Weekly rollup report | MCP / scheduled |
| CS Decision Guide (HTML) | Agents make reship decisions autonomously | Browser access |

## What Jessa Does (3 Steps to Automation)

### Step 1: Fix the Input (This Week)

Jessa enforces Gorgias tagging. Without this, no automation works.

Start with the Gap Analysis: Send Jessa the `gorgias-gap-analysis.md` (already built, in `Cowork/` folder). This document shows her team that only 6% of tickets are being tagged — 94% are invisible to reporting. It has the hard numbers: 1,321 tickets scanned, only 43 properly captured. $1,500-2,500/week in unreported resolution costs.

Jessa's job: Review the gap analysis with her team, identify WHERE the tagging breaks down (which agents, which ticket types, which step in the workflow), and come back with a plan to close the gap. She knows her team better than anyone — let her figure out the "how."

Jessa's action items:

Read the Gorgias Gap Analysis — understand the 94% miss rate and what it costs

Identify the gap: Is it training? Is it the workflow? Is it the Gorgias UI? Is it specific agents? Report findings to Kurt.

Brief her team (Lawrence, Adel, Eli, Mark): "Every ticket needs Contact Reason + Resolution before close. Starting now."

Spot-check 5 tickets/day for 2 weeks — track who tags and who doesn't

Merge duplicate tags (cancel/refund + Cancel Sub + Cancel order → Cancellation)

Confirm agents can access CS Decision Guide in their browser

Report tagging rate to Kurt weekly (target: 50% week 1, 90% week 3)

What Jessa does NOT need to do:

Build reports manually

Count tickets

Track reship costs by hand

Reconcile Slack vs Gorgias

Escalate standard decisions to Kurt

### Step 2: Turn On Auto-Sync (Week 2 — Kurt/AI Assistant)

Once tagging hits 50%+, Kurt's AI assistant configures:

| Automation | Schedule | Output |
| --- | --- | --- |
| Operational issues sync | Daily 6 AM ET | Google Sheet updated |
| Food safety sync | Daily 6 AM ET | Separate tab updated |
| Enrichment (carrier, state) | Daily 6:30 AM ET | Missing fields filled |
| Weekly ops report | Monday 7 AM ET | Summary sheet + Slack post |

Jessa sees: Open Google Sheet Monday morning → full report is there. No manual work.

### Step 3: Live Dashboard (Week 3-4 — Kurt/AI Assistant)

Weekly auto-report in this format:

ELEVATE FOODS WEEKLY CS REPORT — Week of April 7, 2026
Orders shipped: 2,700

ISSUE RATES (normalized to order volume)
  Operational: 46 / 2,700 = 0.85%    (target: <2%)    [OK]
  Food Safety: 25 / 2,700 = 0.46%    (target: <1%)    [OK]
  Arrived Warm: 12 / 2,700 = 0.22%   (trending up)    [WATCH]

CS COST
  Total: $976 = $0.36/order           (target: <$0.50) [OK]

AGENT PERFORMANCE
  Tagging rate: 88% (↑ from 6%)
  Avg response: 3.1 hrs

---

# What Makes Automation Super Easy

## The Unlock: Everything Feeds From 2 Sources

RECHARGE API ──→ Subscription data ──→ Curation Floor ──→ Demand
                                   ──→ Growth Multiplier
                                   ──→ PO Drafts
                                   ──→ Cut Order

GORGIAS API  ──→ Ticket data       ──→ Ops Report
                                   ──→ Food Safety Report
                                   ──→ CS Cost Tracking
                                   ──→ Agent Performance

Both APIs are already connected. The MCP tools already work. The only manual step left is Jessa's team tagging tickets.

## The Automation Stack (What's Running)

| Layer | What | Status |
| --- | --- | --- |
| **Data In** | Recharge sync (subscriptions, charges) | Working — auto-syncs with cache |
| **Data In** | Shopify sync (orders, fulfillment) | Working — EWMA added |
| **Data In** | Gorgias sync (tickets, issues) | Working — needs tagging enforcement |
| **Calculation** | Curation floor (recipe × subs) | Built this session |
| **Calculation** | EWMA + growth multiplier | Built this session |
| **Calculation** | Recipe diff + auto-ramp | Built this session |
| **Output** | PO drafts | Built — `/api/po_draft` |
| **Output** | Cut order XLSX | Existing — needs one-click approve |
| **Output** | Ops report | Tools exist — needs scheduling |
| **Output** | Food safety report | Tools exist — needs scheduling |
| **Decision** | CS Decision Guide | Built — needs team deployment |
| **Decision** | Swap suggestions | Existing — `/api/suggest_fixes` |

## What's NOT Automated Yet (Backlog)

| Item | Effort | Impact | Assigned |
| --- | --- | --- | --- |
| Schedule daily Gorgias sync (cron/Mechanic) | Small | High — enables auto-reporting | AI Assistant |
| Monday Slack post with PO draft + ops summary | Small | High — Tommy + Jessa get alerts | AI Assistant |
| Host CS Decision Guide on Flask app | Small | Medium — browser access for Peak Support | Anik (when available) |
| Fix Mechanic inventory alert loop | Small | Medium — stops 10+/day spam alerts | AI Assistant |
| Anomaly detection (demand deviation >20%) | Medium | Medium — catches surprises | Future sprint |
| Churn detection (Recharge cancellation rate) | Medium | Medium — adjusts forecast | Future sprint |

---

# The Handoff Sequence

## Week 1: Foundation

| Who | Action |
| --- | --- |
| **Jessa** | Brief team on tagging. Spot-check 5/day. Merge duplicate tags. |
| **Kurt** | Share CS Decision Guide with Jessa's team. Confirm browser access works. |
| **Kurt** | Stop answering individual reship tags in Slack. Redirect to Decision Guide. |
| **Tommy** | Start filling vendor catalog (XLSX provided). Define tray recipe SKUs. |

## Week 2: Automation On

| Who | Action |
| --- | --- |
| **Jessa** | Report tagging rate (target: 50%+). Continue spot-checks. |
| **AI Assistant** | Turn on daily Gorgias sync. Configure Monday Slack posts. |
| **Kurt** | Review first auto-generated ops report. Provide feedback on format. |
| **Tommy** | Review first PO draft from dashboard. Approve or adjust. |

## Week 3: Trust Building

| Who | Action |
| --- | --- |
| **Jessa** | Tagging at 90%+. Ops report is accurate. Stop manual spreadsheet. |
| **Kurt** | Cut order is auto-generated. Approve with one click. |
| **Tommy** | PO drafts are reliable. Submit to vendors directly from dashboard. |
| **Kurt** | Leave #reship-and-order-requests channel. Jessa handles it. |

## Week 4: Director Mode

| Who | Action |
| --- | --- |
| **Kurt** | 40 min/week on ops oversight. Rest of time on strategy + systems. |
| **Jessa** | 15 min Monday report review. Rest of time managing her team. |
| **Tommy** | 2 hrs/week procurement. Rest on product planning + cheese rotation. |
| **Test** | Kurt takes a 3-day weekend. Nothing breaks. |

---

# Success Metrics

| Metric | Current | Week 4 Target |
| --- | --- | --- |
| Kurt's ops time | 15-20 hrs/week | <3 hrs/week |
| Jessa's reporting time | 2-3 hrs/week manual | 15 min review |
| Gorgias tagging rate | 6% | 90%+ |
| Shortage lead time | 0-3 days (reactive) | 14+ days (proactive) |
| PO turnaround | Days of Slack DMs | Same-day auto-draft + approve |
| CS cost visibility | Invisible ($1,500-2,500/week estimated) | Tracked to the dollar weekly |
| Shortage incidents | 2-4/week | 0/week |
| Recipe rotation chaos | First-week stockouts | Auto-ramp, zero shortage |

---

# For Dan (if he asks)

The playbook says: "Don't tell Dan to slow down — show him the system that absorbs his speed."

What Dan sees:

Shortages go to zero (system prevents them)

CS costs become visible and trending down

Cut orders happen on time every week

New products (trays) don't break inventory

Kurt has time for strategic projects Dan actually cares about

What Dan doesn't need to know:

The specific automation details (he'll try to redesign them)

That Kurt's role changed (he'll see results, not process)

The delegation framework (it just works)